## Sheet1
Risk number | Risk | Likelihood Score | Conseq Score | Risk Score | Net Score | Justification for the Likelihood score | Justification for the Consequence score | Mitigation (hardware and software) to bring the Risk down from Reds and Yellows to Low Green score | Q1 Behavior (Desired Behavior) | Q2 Behavior (Preventative Behavior) | Q3 Behavior (Responsive Behavior) | Software Requirements Specs (SRS) for Q1 Behavior (Desired Behavior) | Software Requirements Specs (SRS) for Q2 Behavior (Preventative Behavior) | Software Requirements Specs (SRS) for Q3 Behavior (Responsive Behavior) | Test Cases for Q1 Behavior (Desired Behavior) | Test Cases for Q2 Behavior (Preventative Behavior) | Test Cases for Q3 Behavior (Responsive Behavior)
R1 | Behind Schedule | 5 | 4 | 5X4 | 20 | This score was given due to having several vacations planned during the project where I would have limited access to technology | This score was given due to the nature of the project. A lot of the programs rely on previusly built programs/class. This means that a delay in the project sets the whole project back. With that said I also have lighter weeks in terms of school work that I can use to catch up. | A file that holds the milestones and associated due dates. | All milestones and tasks to be completed by their assigned due date. | Working ahead on milestones when one is compleate. | Working tasks within a milestone to ensure they are completed by the milestone deadline and not there personal deadline | N/A | N/A | N/A | Checking Milestones-for-thesis file and seeing the green completed column up to the current date. | Checking Milestones-for-thesis file and seeing that tasks the next milestone are in progress or completed. | Checking Milestones-for-thesis file and seeing that no milestones are in red overdue
R2 | Reprograming | 4 | 3 | 4X3 | 12 | This score was given due to having the big picture planned out but a lot of the implementation not planned. | This score was given due to the flutuating scale of reprograming as a task. Most fixes are likely to be small code changes that should not effect the wider system. | Class testing and black box testing to ensure correctness. | Everything is programed with limited bugs | Programs are tested to ensure correctness | Programs are split into proper modules to ensure that changes do not effect other systems. | N/A | N/A | N/A | N/A | N/A | N/A
R3 | Data Quality | 4 | 5 | 4X5 | 20 | This score was given due to the rushed nature of this project. However research done in previous classes should help validate data. | This score was given due to data being the main product of this project.If the data is of bad quality then there is not much reson for the project to exitst. | data validation using previous research | Data matches observed patterns in the wild | N/A | N/A | N/A | N/A | N/A | Comparing data outputs to datasets of observed predation studies. | N/A | N/A
R4 | Poorly Defined Requirements | 4 | 5 | 4X5 | 20 | This score was given due to the project having very brifly defined requirements. | This score was given due to the project having extreamly limited requirments that have left the project with out a true defanition of successful development. | Software requirment document | Requirements are robust and meet the standards set by IEEE | N/A | N/A | N/A | N/A | N/A | Use IEEE guidelines to ensure requirements are formed correctly | N/A | N/A
R5 | Lack of Developers | 3 | 3 | 3X3 | 9 | This score was given due to the project being designed to be completed by one developer. | This score was given due to the project being designed to be completed by one developer. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A