## Milestones
Task | Status | Expected complition date
Milestone 1: project setup | In Progress | 2026-05-16
GitHub repo setup | Complete | 2026-05-14
Task identification | Complete | 2026-05-15
Project outline | In Progress | 2026-05-16
Not started
Not started
Milestone 2: animal class | Not started | 2026-05-23
Getters/Setters | Not started | 2026-05-18
Functions/Helper fucntions | Not started | 2026-05-22
Thread saftey review | Not started | 2026-05-23
Class tester | Not started | 2026-05-23
Not started
Milestone 3: map class | Not started | 2026-05-30
Singleton pattern review | Not started | 2026-05-26
Getters/Setters | Not started | 2026-05-26
mapping settings | Not started | 2026-05-28
Thread saftey review | Not started | 2026-05-29
Class tester | Not started | 2026-05-30
Milestone 4: movement, pathfinding & energy usage | Not started | 2026-06-13
movment calculations (max speed) | Not started | 2026-06-04
pathfinding algorithm (multithreading) | Not started | 2026-06-11
energy usage calculation | Not started | 2026-06-12
energy total decision | Not started | 2026-06-12
Thread saftey review/implementation | Not started | 2026-06-13
Milestone 5: prey classes | Not started | 2026-06-27
rabbit class | Not started | 2026-06-20
mice class | Not started | 2026-06-24
bird class | Not started | 2026-06-27
Not started
Not started
Milestone 6: predator class | Not started | 2026-07-11
Getters/Setters | Not started | 2026-06-30
hunting/simulation phases | Not started | 2026-07-09
ambush hunting style | Not started | 2026-07-10
pursuit hunting style | Not started | 2026-07-10
reproduction/mutation | Not started | 2026-07-11
Milestone 7: building simulation/data output | Not started | 2026-08-01
building 1 on 1 hunting phases | Not started | 2026-07-24
1 on 1 simulation scaling (multithreading) | Not started | 2026-07-29
Thread saftey review/implementation | Not started | 2026-07-29
mutation chance selection testing | Not started | 2026-07-30
selection of final genertion/end of simulation | Not started | 2026-07-30
building csv output/output formating | Not started | 2026-07-31
signal simulation final testing | Not started | 2026-08-01
data output final testing | Not started | 2026-08-01
Milestone 8: full simulation | Not started | 2026-08-05
multi-simulation (full simulation) testing | Not started | 2026-08-03
full simulation final runthrough | Not started | 2026-08-04
data/output compilation | Not started | 2026-08-05
Not started
Not started
Milestone 9: data analysis | Not started | 2026-08-08
batch data anylsis | Not started | 2026-08-06
building out visuals/graphs | Not started | 2026-08-07
final conclutions | Not started | 2026-08-08
data finalization/formating | Not started | 2026-08-08
Not started
Milestone 10: final outputs | Not started | 2026-08-15
Final project compilation | Not started | 2026-08-15
Final presentation + demo | Not started | 2026-08-15
Final reflection | Not started | 2026-08-15
Not started
Not started

## Helper (hidden)
Status Markers
Not started
In Progress
Complete
Over Due