## Milestones
Task | Status | Expected Completion Date
Milestone 1: project setup | Complete | 2026-05-16
GitHub repo setup | Complete | 2026-05-14
task identification | Complete | 2026-05-15
project outline | Complete | 2026-05-16
Not started
Not started
Milestone 2: animal class | Complete | 2026-05-23
getters/setters | Complete | 2026-05-18
functions/helper functions | Complete | 2026-05-22
thread safety review | Complete | 2026-05-23
class tester | Complete | 2026-05-23
Not started
Milestone 3: map class | Complete | 2026-05-30
Singleton pattern review | Complete | 2026-05-26
getters | Complete | 2026-05-26
mapping settings | Complete | 2026-05-28
thread safety review | Complete | 2026-05-29
class tester | Complete | 2026-05-30
Milestone 4: movement, pathfinding & energy usage | Complete | 2026-06-13
movement calculations (max speed) | Complete | 2026-06-04
pathfinding algorithm | Complete | 2026-06-11
energy usage calculation | Complete | 2026-06-12
energy total decision | Complete | 2026-06-12
thread safety review | Complete | 2026-06-13
Milestone 5: prey classes | Complete | 2026-06-27
rabbit class | Complete | 2026-06-20
mice class | Complete | 2026-06-24
bird class | Complete | 2026-06-26
class testers | Complete | 2026-06-27
Not started
Milestone 6: predator class | Complete | 2026-07-11
getters/setters | Complete | 2026-06-30
hunting/simulation phases | Complete | 2026-07-09
ambush hunting style | Complete | 2026-07-10
pursuit hunting style | Complete | 2026-07-10
reproduction/mutation | Complete | 2026-07-11
class tester | Complete | 2026-07-11
Milestone 7: building simulation/data output | Complete | 2026-08-01
building 1 on 1 hunting phases | Complete | 2026-07-24
1 on 1 simulation scaling (multithreading) | Complete | 2026-07-29
thread safety review/implementation | Complete | 2026-07-29
mutation chance selection testing | Complete | 2026-07-30
selection of final generation/end of simulation | Complete | 2026-07-30
building csv output/output formating | Complete | 2026-07-31
signal simulation final testing | Complete | 2026-08-01
data output final testing | Complete | 2026-08-01
Milestone 8: full simulation | Complete | 2026-08-05
multi-simulation (full simulation) testing | Complete | 2026-08-03
full simulation final runthrough | Complete | 2026-08-04
data/output compilation | Complete | 2026-08-05
Not started
Not started
Milestone 9: data analysis | Complete | 2026-08-08
batch data analysis | Complete | 2026-08-06
building out visuals/graphs | Complete | 2026-08-07
final conclusions | Complete | 2026-08-08
data finalization/formating | Complete | 2026-08-08
Not started
Milestone 10: final outputs | Complete | 2026-08-15
final project compilation | Complete | 2026-08-15
final presentation + demo | Complete | 2026-08-15
final reflection | Complete | 2026-08-15
Not started
Not started

## Helper (hidden)
Status Markers
Not started
In Progress
Complete
Over Due