## Sheet1
Task | Status | Expected complition date
Milestone 1: project setup | In Progress | 2026-05-16
GitHub repo setup | Not started | 2026-05-14
Task identification | In Progress | 2026-05-15
Project outline | In Progress | 2026-05-16
Not started
Not started
Milestone 2: animal class | Not started | 2026-05-23
Not started
Not started
Not started
Not started
Not started
Milestone 3: map class | Not started | 2026-05-30
Not started
Not started
Not started
Not started
Not started
Milestone 4: movement, pathfinding & energy usage | Not started | 2026-06-13
Not started
Not started
Not started
Not started
Not started
Milestone 5: prey classes | Not started | 2026-06-27
rabbit class | Not started
mice class | Not started
bird class | Not started
Not started
Milestone 6: predator class | Not started | 2026-07-18
Not started
Not started
Not started
Not started
Not started
Milestone 7: test simulation/data output | Not started | 2026-08-01
Not started
Not started
Not started
Not started
Not started
Milestone 8: full simulation | Not started | 2026-08-05
Not started
Not started
Not started
Not started
Milestone 9: data analysis | Not started | 2026-08-08
Not started
Not started
Not started
Not started
Milestone 10: final outputs | Not started | 2026-08-15
Final project compilation | Not started | 2026-08-15
Final presentation + demo | Not started | 2026-08-15
Final reflection | Not started | 2026-08-15
Not started
Not started

## Sheet2
Status Markers
Not started
In Progress
Complete
Over Due